## Slide 1: Plano de Ação Anual (PAA)
The Annual Action Plan of a public body: written by its units, approved by its directorates, paid for by its budget, carried out and reported through the year
Implemented by G-Kakaroto
Notes: The application is the Annual Action Plan. Everything else, approval, budget, execution and reports, exists to write the plan, approve it, pay for it, carry it out and report on it. It is not tied to one institution; the Ministry of Transport and Communications appears only as a sample dataset.

## Slide 2: What the Annual Action Plan is
What
The activities of the year, under the programme and subprogramme they serve.
Who
The unit that owns each activity, and the person responsible.
When
The quarters it runs in and the months of each of its actions.
With what
The budget lines by economic category, each with its funding source.
How we will know
Indicators with a baseline and a target, reported month by month and quarter by quarter.
Notes: The PAA answers five questions for each unit: what will we do, who is responsible, when, with what means, and how will we know. Every activity of the plan carries those five answers, and the whole application keeps them together.

## Slide 3: Everything in the application serves the plan
The Annual
Action Plan
(PAA)
Units write it
Activities, indicators, actions, budget lines
Directorates approve it
Prepare, certify, approve; named approvers
Directorates finalize it
Each head ends planning for their own plan
The budget pays for it
The envelope received, shared over the approved plan
Units carry it out
Monthly spending and quarterly indicators, verified
Reports show it
The plan and its results in the Ministry of Finance form
Notes: The plan is at the centre. Units write it, directorates approve and finalize it, the budget received pays for it, units carry it out and report on it, and the reports are the plan and its results in the formal template. Every step is in the audit record.

## Slide 4: The year of the plan
1
Write
Units draft activities and submit them while the submission window is open.
2
Approve
Each activity is prepared, certified and approved by the heads of its directorate.
3
Finalize
Each directorate's head finalizes the plan of their own directorate.
4
Fund
The institution registers the envelope it receives and shares it over the approved plan.
5
Carry out
Units report spending and indicators inside the monthly and quarterly windows.
6
Report
Others verify, directors compile the quarter, and the reports are printed.
Notes: The life of the Annual Action Plan over the year. Planning ends per directorate; the whole year's planning ends when every directorate that planned has finalized, or when the envelope is received. The plan cannot be reopened after the envelope; only its distribution changes.

## Slide 5: One page shows where the plan stands
The Plan cycle page, fiscal year 2027, with the sample dataset
Windows
The administrator sets the dates for plan submission and for each month and quarter. No dates means open; an administrator can always act.
Always current
Approval progress, the budget and the reporting status are read live; nothing is typed in by hand.
Where things are done
Buttons to report execution, compile the quarter and open the printed reports.
Notes: The Plan cycle page and the dashboard show the same six steps and which one is current. Windows are set by the administrator; with no dates a window is open.

## Slide 6: What an entry of the plan contains
Programme
OGE code, name, objective. Set up once for the year by the administrator.
Unit
The directorate or unit that owns the work and has its own people.
Activity
What will be done in the year: description, priority, the quarters it runs in, dates, the person responsible. Starts as a Draft.
Indicators and actions
A target and a baseline, with the numbered actions that carry it out and the months each takes place in.
Budget lines
An amount by economic category with a funding source, optionally tied to the indicator it pays for.
An activity can be submitted when
It has a budget line with an amount
It has an indicator with a target
The dates are in order and the window is open
Notes: A programme and its units exist first. A unit creates an activity under a programme, gives it indicators with numbered actions and months, and budget lines with a funding source, each optionally tied to an indicator. The system refuses to submit an incomplete activity.

## Slide 7: Each unit writes its own part of the plan
The activities of the plan: filters, tabs and status chips
Its own people
Each unit has a planner and a director; what a person sees and writes follows their unit.
Copy last year
Start from the previous plan as drafts, once; review, adjust and submit.
Import and export
Load activities from a CSV file (checked line by line) and export the plan.
Notes: Every unit has its own people: a planner who prepares and a director who certifies. A unit sees its own activities and those of the units below it. Tabs separate drafts and returned work, activities in review, approved ones, and the ones that need my action. At the start of a year the previous year's plan can be copied as drafts, once.

## Slide 8: Prepare, certify, approve
1
Draft
The unit
Completes the activity, its indicators and budget lines.
2
Prepared
Planner or director
Submits it once it passes the checks.
3
Verified
Director of the unit
Certifies it; where a unit above validates, it goes up.
4
Certified
Director of the unit above
Validates the plans of the units beneath.
5
Approved
Head of the directorate
Gives the final approval of the plan of their own directorate.
Returned with a reason
At any step a reviewer sends it back; the unit sees why, corrects it and submits again.
Locked once approved
An approved activity is not edited. Reopening it needs a written reason.
Every step is on record
Who, when and any note are kept in the history; many can be approved at once.
Notes: Statuses: Draft (being prepared), Prepared (submitted), Verified (certified by the unit's director, where a unit above validates first), Certified (validated), Approved. The head of the top-level unit gives the final approval; the Minister does not approve plans. A return needs a reason; an approved activity is locked and can be reopened with a reason until the envelope is received.

## Slide 9: One inbox for everything waiting on the plan
Approvals: what is waiting for you, each with a link
Decide
Certify, approve or return with a reason, one by one or many at once; each is checked again as it is written.
Verify
Execution figures wait for someone other than the person who reported them.
Finalize
Each head is told when their directorate's plan is ready to be finalized.
Notes: Approvals is one page with everything waiting for the person: activities to decide, execution figures to verify (never their own), the plan ready to be finalized for the directorates they head, budget steps, and their own drafts and returned work. The dashboard's Needs your attention is the same list.

## Slide 10: Named approvers, interim cover and reshuffles
Approval lists
Name who prepares, certifies and approves the activities of a unit.
The nearest list above a unit applies to the units below it.
No list: the default rule (the director) stays.
Interim approvers
Someone stands in for a director between two dates.
They certify and approve for the unit, even where a list names other people.
It ends on its date, or when revoked.
Reshuffles
Move a unit to another parent: the heads and lists above take over, pending work follows.
Replace one person by another in every list at once.
An administrator can move an activity to another unit, with a remark.
Notes: A director keeps the list of people who prepare, certify and approve for their units. The nearest list above a unit applies. An interim stands in for a director for dates; they certify and approve but do not prepare. A reshuffle needs no clean-up because authority is worked out from the tree and the lists at the moment someone acts.

## Slide 11: Everyone signs in order, and nothing is ever erased
Signing in order
1
Ana signs first
2
Bento signs second
3
Carla signs last
The activity is approved only after the last signature. An interim signs in the place of the next name; administrators are never held up.
Rounds and the record
Round 1
Ana signed, Bento signed. Carla returned the activity with a reason.
Both signatures: voided (by Carla, with the reason). Kept.
Round 2
The unit corrected it. Ana, Bento and Carla sign again, in order.
Approved. All six signatures stay in the history.
Signatures are never deleted: each belongs to a numbered round and is completed or voided, with who and why. Every change is also in the audit log.
Notes: A certify or approve list of two or more people can sign in order: each in turn, and the activity moves on only after the last signature. If the activity is returned or reopened, a new round starts and the earlier signatures stay on record, marked as voided with who voided them and why. The history tab shows every signature of every round, so who signed before a reset can always be told.

## Slide 12: Each directorate finalizes its own plan
The banner counts the directorates that have finalized
Finalized by the head
When everything in the directorate is decided, its head finalizes the plan, with a remark.
The others go on
A finalized directorate takes no new activities; the other directorates keep planning.
Reopened with a reason
Only the head or an administrator, only before the envelope is received. All of it is in the audit trail.
Notes: The head of each top-level unit finalizes the plan of their own directorate once nothing in it waits for a decision. A finalized directorate takes no new activities, imports or roll-forward copies for the year; the others keep planning. The year ends when all directorates that planned have finalized, or when the envelope is received; the plan can be reopened by the head or an administrator, with a reason, only before the envelope.

## Slide 13: The budget pays for the approved plan
The fiscal envelope with its distribution by economic category
Register and approve
The envelope with its reference, dates and total, divided by economic category.
Distribute over the plan
Approved activities only: capped at what each line asked for, to the cent, in one transaction.
Review
Budget allocation and the allocation review show what each unit and programme received.
Notes: The envelope is what the institution receives: the State Budget allocation for a ministry, an allocation from the ministry for a directorate. It is registered with its reference and approved. The distribution uses approved activities only, never gives a line more than it asked for, is exact to the cent and runs in one transaction. A surplus stays unallocated.

## Slide 14: Carrying out the plan: report, verify, compile
Monthly spending
Committed and paid for each budget line, inside the window of the month.
Quarterly indicators
Progress against each target, in the quarters its months fall in.
Narratives
Results achieved and constraints, for each month and each quarter.
Verified by someone else
Nobody verifies their own report; only verified figures reach the reports.
Windows
A period outside its window cannot be reported; administrators always can.
Compile the quarter
A draft from what the units reported, edited by the director into the text of the report.
Notes: Each month the unit reports committed and paid per budget line. Each quarter it reports the indicators. Every month and quarter has a narrative. Figures count only once someone other than the reporter verifies them. Directors compile the quarter: the system drafts the text from what the units reported and the director edits and saves it.

## Slide 15: The plan and its results, in the Ministry of Finance form
Final plan report: complete or summary
Implementation plan of a unit, with actions and months
Also: the performance report (monthly or quarterly) with the narratives and the verified figures; CSV export of the activities and of the report data.
Notes: Three printed forms follow the formal template: the final plan report (complete or summary), the implementation plan of a unit with its actions and the Jan-Dec grid, and the performance report monthly or quarterly. A4 landscape, programme and subprogramme bands, print or PDF. The final plan report is of the plan; it is not addressed to anyone.

## Slide 16: Everyone sees and does what their role allows
Administrator
Sets up the institution, users, windows and settings; can always act.
Minister
Sees every plan and approves the fiscal envelope.
Director
Certifies; the head of a directorate gives its final approval and finalizes its plan.
Planner
Prepares activities, indicators and budget lines, and reports execution.
Finance
Confirms budget lines and verifies the spending that units report.
Viewer
Reads plans and reports; changes nothing.
Notes: Six roles. The Minister sees every plan and approves the fiscal envelope but does not approve plans. The head of a directorate approves their own directorate's plans. Finance confirms budget lines and verifies spending. Permissions are checked on the server for every action.

## Slide 17: A professional, accessible interface
The dashboard: the plan's cycle, key figures and what needs your attention
Clear at a glance
The plan's cycle, the figures and your own to-do list on one page.
Three languages
English, Portuguese and Tetum; a test blocks any new text without its translations.
Made for the role
The menu, the buttons and the inbox show only what your role can do.
Notes: Compact tables, status chips with a dot and a word, figures that line up. Automated accessibility checks pass on every screen, and every text exists in English, Portuguese and Tetum.

## Slide 18: Built for any institution, whole ministry or one office
Institution
Directorate
Units, each with its people
Gabinete
Units, each with its people
Autonomous body
Units, each with its people
Any depth the law defines
One deployment, one institution
Name, structure and programmes are set in the app; nothing is hard-coded to a ministry.
Whole ministry or a single office
Start with one directorate or gabinete and add the rest later.
Autonomous bodies included
Public bodies with their own legal personality sit in the same tree.
Notes: The Ministry of Transport and Communications is only a sample. A deployment serves one institution; you can start with a single directorate or office and add the rest later. Each directorate and unit has its own users.

## Slide 19: Controls an institution can rely on
Audit trail and record
Every change, and every signature of every round, with who and when. Nothing is erased.
Role permissions
Checked on the server for every action, not only hidden in the menu.
Two-factor sign-in
Authenticator codes and recovery codes; required for senior roles.
Closed registration
No self-sign-up; sign-in attempts are rate-limited.
Backups and health
Nightly verified backups and a health check for uptime monitoring.
Tested
375 automated tests guard the approval and budget rules.
Notes: The audit log records every change with who and when. Permissions are checked on the server. Two-factor sign-in, closed registration, nightly backups, and 375 automated tests that guard the approval and budget rules.

## Slide 20: Try it with sample data
A whole ministry
The Ministry of Transport and Communications with its directorates, municipal directorates and autonomous bodies; the real State Budget plans for 2025 to 2027 and a planner and a director for every unit.
Practise the real flow
Sign in as a planner, a director and the head of a directorate and follow an activity from draft to approved, with the lists, interim cover and signing in order.
Loaded and removed by an administrator at Management > Sample Data; real data is never touched. Refused in production.
Notes: An administrator loads the optional sample at Management, Sample Data: a ministry with its directorates, municipal directorates and autonomous bodies, each with its planner and its director. Purging removes only the sample.

## Slide 21: Proposed next steps
1
Deploy for real use
Production server, queue worker for notifications, Redis for sessions and cache, and the nightly backup job.
2
Pilot with one directorate
Load the real structure and people, set the windows, and run one full plan with its own planners and director.
3
Train with the manual
The user manual walks every role through the whole year; sample data lets people practise first.
4
Keep improving
Watch real usage, fix what real users hit, and keep every text translated.
Notes: Close with the ask: agree the pilot directorate and the deployment date.